# National Strategic Clinical Network for Maternity and Neonatal Services

# Workplan 2024/25

# Background

## 1.1 	Strategic Network background

Whilst the Maternity and Neonatal Strategic Clinical Network was formally established on the 1 April 2024, there has been a well-established maternity and neonatal network in Wales since 2019.

The Strategic Network aim is to improve outcomes and experience for all mothers, babies and their families with the knowledge that giving every child the best start in life is crucial to reducing health issues. There is strong evidence that suggests the period during pregnancy and up to the child’s second birthday (the first 1,000 days) offers the greatest potential for impact in both improving long term outcomes and reducing inequalities.

The key responsibilities of the network prior to 1st April 2024 included:

- Co-ordinating the development of sustainable and equitable maternity and neonatal services to ensure all Welsh mothers and babies receive appropriate care provided by skilled, trained staff

- Develop and implement consistent pathways for maternity and neonatal care across Wales

- Ensure that the input of parents and families is valued and considered in all aspects of the Network's work

- Ensure a high-quality service is provided for Welsh mothers and babies by overseeing appropriate audit of clinical practice and the development of joint learning opportunities and the sharing of good practice.

Pregnancy and childbirth are life-changing events for women, birthing people, their partners and their families. It is a time of new beginnings, both momentous and often eagerly anticipated. This time in a family’s life is so important in shaping the lives of babies, parents, families and communities forever.

Around 28,000 babies are born each year in the 26 maternity units across Wales. Around nine to ten per cent of these will need admission to a neonatal unit, of which there are nine in Wales providing a range of different levels of neonatal care.

The Maternal, Newborn and Infant Clinical Outcome Review Programme report on UK perinatal deaths of babies born in 2022 highlights the latest clinical outcomes as follows:

- The Welsh number of stillbirths per 1,000 total births was 3.63 which whilst reduced from 2021 number is still higher than the UK overall rate of 3.35

- The Welsh number of neonatal deaths per 1,000  births was 1.91 which is higher than the UK overall rate of 1.69

Across Wales we have high rates of obesity and these have doubled in the last decade. Pregnant women with high BMI increases the risk of complications and could have a detrimental impact on clinical outcomes for both the mother and baby.

A number of high-profile maternity and neonatal reports have been published over the last few years and have highlighted poor outcomes and experiences of babies and women and the long-lasting effects that these have upon individuals, families and communities. The significance and findings of these reports challenges and holds all stakeholders involved in the provision of maternity and neonatal service to drive improvement in quality and planning services and to ensure we have systems that can provide effective quality assurance to improve our clinical outcomes in Maternity and Neonatal Services in Wales.

## 1.2 	Strategic Network Governance

The following diagram provides an overview of the Maternity and Neonatal Strategic Network governance. The Network has been structured with an overarching Network Leadership Team and a Clinical Reference Group. The work of the Network has been split into two reporting structures: the Implementation Network to oversee and lead the work of the Maternity and Neonatal Safety Support Programme and then a corresponding arm overseeing the priorities and actions of the strategic network including development of service specifications; clinical pathways and quality assurance. The Network is supported by a number of advisory groups.

At the time of writing the Strategic Network Leadership Group is being formed now the Network Manager has commenced in post. The Strategic Network has successfully transitioned its meeting structure from its previous structure and the Clinical Reference Group has met twice in 2024/25 and a number of the advisory groups have also met.

## 1.3 	Strategic/Policy Drivers

The Perinatal Quality Statement is currently in development by Welsh Government and once published (expected Autumn 2024) will provide the guiding strategic context for the Maternity and Neonatal Strategic Network. The Strategic Network will develop a perinatal service specification to define the standards expected from services and key quality measures and outcomes to be monitored.

The Maternity and Neonatal Strategic Network will ensure the aims and objectives of the key overarching strategic and policy drivers in Wales are met, for example:

| Strategy/Policy | Summary | How the Maternity and Neonatal Strategic Network will support: |
| --- | --- | --- |
| NHS Wales Planning Framework 2024 – 2027 | Sets out the statutory planning direction for NHS organisations for the coming year, looking ahead to the following 3 years. Guidance outlines the key drivers to achieve change with a focus on digital opportunities, reducing inequalities especially for women and children, national programme priorities as well as work streams of the value and sustainability. The Planning Framework has a strong focus on ‘Once for Wales’ particularly to support key enablers such as implementing workforce and digital solutions at a national system wide level. | The Strategic Network work programme includes development of service specifications and a perinatal dashboard to support the measurement and monitoring of clinical outcomes. A key enabler and priority for the strategic Network is the implementation of a digital maternity record across Health Board in Wales. These products will enable a focus on reducing unwarranted clinical variations and identify priorities to reduce inequalities. Supporting the implementation of the Maternity and Neonatal Engagement Framework will ensure the Strategic Network focus on assuring attainment of outcomes that matter. |
| A Healthier Wales: Our Plan for Health and Social Care (June 2018) | ‘A Healthier Wales’ is the Welsh Government’s response to the Parliamentary Review. It sets out the vision of a ‘whole system approach to health and social care’ which is focused on health and wellbeing, and on preventing physical and mental illness. It focuses on ‘providing more joined-up services, in community settings’, and shifts the emphasis from treating illness to prevention and supporting people to stay well and lead healthier lifestyles. It includes the focus on the quadruple aim. | The Strategic Network will provide the vision and service specification for Maternity and Neonatal services across Wales which will focus on the whole system and supporting women and birthing people to stay well and lead healthy lifestyles. The Strategic Network will work with partners across the whole system of health and social to contribute to the improvements required in the first 1,000 days of a child’s life to contribute to longer term improved clinical outcomes. |
| The Wellbeing of Future Generations (Wales) Act 2015 | The Wellbeing of Future Generations Act is about improving the social, economic, environmental, and cultural wellbeing of Wales. It makes the public bodies listed in the Act think more about the long-term, work better with people and communities and each other, look to prevent problems and take a more joined-up approach. | The Strategic Network long term plan focuses on: - Addressing health inequalities. - Improving clinical outcomes for women; birthing people and babies by focusing on quality improvement - Working in collaboration and partnership with all stakeholders across the system - Engagement; involvement and co-production of improvement with families |
| #### National Clinical Framework: A learning health and care system | The framework outlines the future clinical model with a clear focus on Population health, quality and safety, pathways, prudent health care and outcomes. The National Clinical Framework will be delivered through key enablers: Clinical Networks, National Programmes, workforce strategy and digital strategy. | The Strategic Network is a key enabler for the framework with its work programme focused on developing and implementing a whole system service specification. This will ensure clear and consistent clinical pathways and incorporate the system wide learning to ensure improvement in quality; safety and a system to monitor clinical outcomes. Two key enablers for the Strategic Network is the publication of the Perinatal workforce strategy and progress and implementation of the digital maternity record. |
| #### The Duty of Quality | The Health and Care Quality Standards provide a high-level framework to help us plan, make decisions, deliver and monitor health services in NHS Wales. The 12 Health and Care Quality Standards are intended to apply broadly to the wide range of services provided by the NHS in Wales. These standards are Safe; Timely; Effective; Efficient; Equitable; Person-centred; Leadership; Workforce; Culture; Information; Learning; Improvement and Research; Whole systems approach. | The Strategic Network through the Quality Statement and Service specification will be clear about what good look likes in Maternity and Neonatal services and will ensure there is a system to monitor how services are being delivered through a quality lens. |

In addition, there are some service specific Maternity and Neonatal independent reviews and corresponding strategic and policy drivers which will inform the vision; aims and objectives of the Maternity and Neonatal Strategic Network and corresponding work programme. These include:

| Specific Maternity and Neonatal strategy/policy drivers | Summary | How the Maternity and Neonatal Strategic Network will support: |
| --- | --- | --- |
| Maternity Care in Wales A five year vision for the future (2019-2024) | Person-centred, safe, and high-quality care has a positive impact on the health and life chances of women, birthing people and babies and on the healthy development of children throughout their life. The strategy champions the provision of the safest possible, equitable maternity care in Wales, so that all users can trust the care they are offered and have the best outcomes, regardless of post code. It sets out the vision that: “Pregnancy and childbirth are a safe and positive experience, and parents are supported to give their child the best start in life”. | The Strategic Network will develop and implement the service specifications to support maternity and neonatal services to be person-centred; equitable; safe and provide high-quality care. The Strategic Network will ensure there are systems to monitor clinical outcomes which are focused on the quality of services and improvement programmes to support improvement in outcomes regardless of postcode or ethnicity. The Strategic Network will support the Maternity and Neonatal Engagement Framework so the experience and voice of the women; birthing people; and their families is central to the work programme priorities. |
| HIW National Review: Maternity Services (November 2020) | HIW, as part of their ‘National Review of Maternity Services found that across all health boards there were patient safety issues which raised concerns over local management, governance and staffing. It identified several recommendations which included a single patient record, new dashboards and electronic tools to monitor clinical performance and governance, improvements to patient records, and support to improve staffing levels where there are acute shortages | The Strategic Network is supporting a key enabler through the development of the digital maternity record and alongside this is developing the perinatal dashboard and implementing systems to monitor and improve clinical performance and governance. The Strategic Network is supporting a key enabler with HEIW and the development of the Perinatal Workforce Strategy and this will inform the staffing recommendations within the service specification. |
| Improving Together for Wales Maternity Neonatal Safety Support Programme Cymru (July 2023) | Following some of the independent reviews of Maternity Services in Wales as well as the findings from the HIW report and some of key learning reports on Maternity and Neonatal services across the UK, Welsh Government commissioned Improving Together for Wales. This report explores the landscape of maternity and neonatal services in Wales and was broad in its remit, including detailed views of work culture, leadership and learning alongside workforce and clinical outcome measures for mothers and babies across the nation. The report identified a number of recommendations and with an aim "that services for mothers, babies and their families continually improve to ensure that every family in Wales receives care that is always the best it can be, equitable and safe". | The Strategic Network will be responsible for the implementation of phase 2 of the Safety Support Programme. This will require close collaboration and effective partnership working with a number of system wide stakeholders. The recommendations require personal, local, regional and national actions – along with systemic change, a sustained co-ordinated approach to improvement, and strong collaborative leadership. |

## Key NHS Exec/System Stakeholders

Stakeholders for the Maternity and Neonatal Strategic Network will include NHS Executive directorates, NHS Wales delivery organisations, the Joint Commissioning Committee; Welsh Government, third sector, patient/family representatives and wider public represented through Llais; governing bodies; academic and research institutions and in some cases, partners in industry. Due to the geography of Wales and patient flows as well as location of specialist centres there are also key stakeholders with NHS England delivery organisations and associated networks.

Our stakeholders have a key role in providing clinical expertise to inform best practice, assess evidence and current service provision and to inform the longer-term planning of services. The Maternity and Neonatal Strategic Network will be key partners in agreeing whole system standardised approaches and implementation of standards and care pathways to improve the quality of care provided across maternity and neonatal services.

An initial mapping of relevant stakeholders has been undertaken by the Network Manager and described as follows:

Plans are in place as part of the Network Manager’s induction to meet with the NHS Executive communication leads to develop a comprehensive stakeholder map and undertake stakeholder analysis to inform the strategic network communication plan and medium-term planning.

# 2. 	Identifying annual priorities (2024/25) towards the longer-term vision

## 2.1 	Identifying long-term vision and outcomes

As highlighted in other sections of this document there has been a number of high-profile maternity and neonatal reports, both from across the UK and also reviewing the services provided in Wales and the corresponding experience and outcomes for babies; women and their partners and families. These reports have highlighted poor outcomes and experiences as well as inequalities in care and the long-lasting effects that these have upon individuals, families and communities. NICE; British Association of Perinatal Medicine and the relevant Royal Colleges (e.g. Royal College of Obstetrics and Gynaecology; Royal College of Midwifery and Royal College of Paediatrics and Child Health) have also published standards for maternity and neonatal services. As a result of these reports and standards, there have been a number of whole system improvement recommendations and actions instigated for maternity and neonatal services at a local; regional and national level in Wales and in the UK.

In particular, the former Improvement Cymru led on the MatNeo Safety Support programme (MatNeo SSP) discovery phase and identified a number of recommendations and actions required to improve the quality of maternity and neonatal services.  The MatNeo SSP is intended to be a three-year programme and some examples of the priorities within the programme to improve long term outcomes include:

- To support maternity and neonatal services in Wales to reduce maternal  and neonatal morbidity and mortality

- Avoiding unnecessary term admission to neonatal units by implementing the baby care bundle

- Reducing neonatal harm from acute deterioration and reducing separation of mother and baby

There is therefore a significant wealth of discovery data and themes to inform the longer-term vision and objectives for Maternity and Neonatal services in Wales. Within the workplan for 2024/25 the strategic network aims to triangulate all of these reports and recommendations with assessment of system data and outcomes to help develop and build on the medium and longer-term planning for the strategic network.   The Strategic Network also has good networks with equivalent organisations across the UK and will look to benchmark and learn from the experiences and knowledge in England and Scotland in particular.

Alongside these reviews and policy documents, there are also some clear guidance and standards set by the British Association of Perinatal Medicine in relation to the provision of neonatal care to support high quality clinical outcomes. The current service provision for the specialist elements of neonatal care is planned for by the Joint Commissioning Committee (JCC), on behalf of the Health Boards in Wales. As a result of some of the outcomes from reviews and standards, the JCC is taking forward a programme of work to undertake strategic planning on the neonatal service model across South Wales and designation of cots across Wales. This programme of work is anticipated to run from 2024 to approximately 2027 and it is expected will result in service change across Wales. This is a clear interdependency to the Strategic Network medium and longer-term plans.

## 2.2 	Identifying priorities and actions for 2024/25

The following work plan describes the key high-level priorities and actions of the 2024/25 annual plan for the Maternity and Neonatal Strategic Plan. It reflects the priorities identified in the mandate from Welsh Government which are described as follows:

- Quality Planning - As the Strategic Network awaits the publication of the Quality Statement, work has progressed and is planned on developing the perinatal service specification in phases.

- Quality Improvement - The Strategic Network is responsible for the implementation of phase 2 of the MatNeo Safety Support Programme (SSP) and is working closely in collaboration with the Quality, Safety and Improvement team in the NHS Executive with this priority.

- Quality Control - There is also ongoing development of the systems and processes required to review pathway and outcome data and provide quality assurance and governance.

The workplan sets out the actions planned by the Strategic Network and has been themed these under three key priorities:

- Priority 1 – Implement the Maternity and Neonatal Strategic Network – this includes the actions required to implement the strategic network effectively including recruitment into some of the key clinical and enabling administrative positions as well as actions to inform the development of the longer-term priorities and requirements of the Network to inform the medium term work programme;

- Priority 2 - Development of the Maternity and Neonatal strategic network work programme to develop service standards and evaluate the implementation of All Wales guidelines; development of specifications and family integrated care pathways for specific areas and provide quality assurance and learning nationally through the development of perinatal dashboards; shared learning events and escalation documents. The Network will be working closely with the Performance and Assurance teams in the NHS Executive in some of these actions and priorities;

- Priority 3 - Implement Phase 2 of the Maternity and Neonatal Safety Support Programme. This includes supporting the transition of the programme and close working with the Quality, Safety and Improvement Directorate. The focus for the Network includes implementing improvement actions for the maternal care pathway; recognition and escalation of the deteriorating patient and perinatal optimisation and management of the neonate. The Maternity and Neonatal Safety Support Programme includes a number of actions that are being lead by other organisations for example through HEIW; DHCW and Local Health Boards. The Implementation Network will have oversight of the key stakeholder actions.

The 2024/25 work plan actions are required to inform the medium-term work programme and will enable the agreement of standards and systems for monitoring outcomes and identifying unwarranted variation.

| Priority: Strategic/ policy drivers | Quarter | Network actions | Measure | Collaborative working |
| --- | --- | --- | --- | --- |
| Priority 1 Implement the Maternity and Neonatal National Strategic Clinical Network - A Healthier Wales - National Clinical Framework | Quarter 1 (April -June) | - Recruitment: Network Manager and Clinical Lead start in post and have undertaken induction programme - Architecture: establishment of the strategic network meeting structures (e.g. Clinical Reference Group and Clinical Advisory Groups) to replace the advisory network meeting structures - Workplan: initial development of proposed network workplan for 2024/25 and sign off | - Roles started in post - Induction completed - Meeting architecture established and dates in diary with agreed terms of reference - Network workplan for 2024/25 agreed | - HR and OD, Network and Planning Directors - Networks directorate - Finance - Stakeholders - Communication team - Joint Commissioning Committee - Health Boards |
|  | Quarter 2 (July-Sept) | - Network Resources: Agree network budgets and expected forecasts including agreed infrastructure to support workplan - Network Resources: recruit to clinical posts and additional staff to support the strategic network and implementation of the Maternity and Neonatal Safety Support Programme Phase 2 (MatNeo SSP) - Workplan: strategic review of relevant reports and key recommendations and current system information to support the development of the network medium term workplan and interdependencies of recommendations with other teams internally and externally (e.g. HEIW; DHCW) - Communications: induction meetings with network team and key stakeholders to inform stakeholder analysis - Architecture: establish the Clinical Leadership Group and dates to align with the network meeting structure - Transition from network responsibilities for transport: support the Joint Commissioning Committee (JCC) on their development of options for exit strategy for neonatal transport | - Accountability letter received - Budget forecast complete - Roles started in post - Induction completed - Stakeholder mapping - Triangulation and assessment of key themes and recommendations from key reports with system information - Terms of reference of Leadership group agreed and agreed dates in diary - Options developed by JCC to inform exit strategy for network hosting neonatal transport service provision in South Wales |  |
|  | Quarter 3 (Oct-Dec) | - Recruitment: additional staff start in post and have undertaken induction programme. - Network Resources: Review network budget and forecast against planned spend for objectives defined in work plan. - Network Resources: structured programme designed to support the network team development and commenced - Workplan: draft the network medium term workplan in collaboration with key stakeholders - Communications: development of a communication plan - Transition from network responsibilities for transport: oversee and support the JCC on their appraisal and decision to inform a preferred and agreed option for the future operational delivery host for neonatal transport | - Roles started in post - Updated budget forecast - Team development programme commenced - Draft medium term workplan - Communication plan developed - Preferred option agreed by JCC to inform exit strategy for network hosting transport service provision in South Wales |  |
|  | Quarter 4 (Jan-Mar) | - Network Resources: continuation of network team development programme - Network Resources: Review the network budget and forecast with priorities of network to inform medium term workplan - Workplan: submission of an agreed medium term network plan to the NHS Executive - Communications: implement the communication plan - Transition from network responsibilities for transport: implement the exit strategy and hand over for neonatal transport | - Team development continued - Medium term plan co-produced including financial analysis and submitted to WG with supporting annual plan for 2025/26 - Communication plan implemented with development of sharepoint and website - Implement exit strategy and hand over for neonatal transport |  |
| Priority 2 Development of the Maternity and Neonatal strategic network work programme to develop service standards; specifications and family integrated care pathways and provide quality assurance and learning | Quarter 1 (April -June) | - Quality control design and development of quality standards/indicators/measures to inform the development of National Perinatal Dashboard - Quality control Undertake review of HB compliance with published All Wales guidelines - Quality control development of a perinatal escalation plan aligned with in-utero transfer guideline - Quality Planning Perinatal Service Specification undertake review of transitional care provision across Wales - Quality Planning Family Integrated Care Pathways Undertake review of HB compliance with the BAPM recommendations for Family Integrated Care - Quality Planning Family Integrated Care Pathways Embed the evidence-based care bundle PERIPrem Cymru into clinical practice | - Agreed initial quality indicators/measures for the National Perinatal Dashboard - Development of perinatal escalation plan - Completed review of transitional care provision - Completed review of compliance with BAPM recommendations for Family Integrated Care | - DTIV (NHS Executive) - Performance and Assurance (NHS Executive) - Financial Planning and Delivery (NHS Executive) - Quality, Safety, and Improvement (NHS Executive) - HEIW - Public Health Wales (Prevention) - DHCW - Bereavement charity - Health Boards - WAST - WG |
|  | Quarter 2 (July-Sept) | - Quality control/improvement further development and implementation of phase 1 of National Perinatal Dashboard - Quality control Complete review of HB compliance with published All Wales guidelines and resulting recommendations - Quality control ratification and implementation of a perinatal escalation plan aligned with in-utero transfer guideline - Quality control/improvement commence scoping of single point of contact cot and maternal bed locator including labour/triage line - Quality planning Perinatal Quality Statement support WG with the analysis of responses from consultation of the quality statement to inform final statement - Quality planning Perinatal Service Specification commence task and finish group to develop the transitional care service specification - Quality planning Family Integrated Care Pathways evidence-based care bundle PERIPrem Cymru implemented into business as usual within clinical practice - Quality planning Family Integrated Care Pathways commence the development of the national bereavement care pathway for Wales | - Implementation of phase 1 of National Perinatal Dashboard - Completed review of HB compliance with published All Wales guidelines - Implementation of agreed perinatal escalation plan - Analysis of responses from consultation on the quality statement - Task and finish group established with agreed terms of reference and membership - Implementation of PERIPrem Cymru as business as usual |  |
|  | Quarter 3 (Oct-Dec) | - Quality control/improvement scoping and development of quality indicators/measures and agreed definitions to inform phase 2 of National Perinatal Dashboard - Quality control Implementation of any recommendations following review of compliance with All Wales guidelines - Quality control/improvement completion of the scoping of single point of contact cot and maternal bed locator including labour/triage line and options/recommendations for next steps - Quality planning Perinatal Quality Statement support WG with the launch of the quality statement - Quality planning Perinatal Service Specification completion of the task and finish group and proposed draft transitional care service specification for consultation | - Agreed phase 2 quality indicators/measures for the National Perinatal Dashboard - Implementation of recommendations for All Wales guidelines - Options and recommendations for next steps for development of single point of contact national cot and maternal bed locator - Launch of the Quality Statement - Proposed draft transitional care service specification for consultation |  |
|  | Quarter 4 (Jan-Mar) | - Quality control/improvement implementation of phase 2 of National Perinatal Dashboard - Quality control/improvement Undertake formal evaluation of the impact of the PERIPrem Cymru Programme on outcomes - Quality control commence scoping on the development of a peer review programme for perinatal services - Quality control/improvement Host Quality Improvement & Audit event in collaboration with Quality, Safety & Improvement colleagues - Quality control/improvement Implementation of the service user engagement framework - Quality planning Perinatal Service Specification transitional care service specification approved for implementation - Quality planning Family Integrated Care Pathways completion of a proposed draft of the national bereavement care pathway for Wales for consultation - Quality planning scope out the requirements for Maternal medicine network | - Implementation of phase 2 of National Perinatal Dashboard - Evaluation of impact of the PERIPrem Cymru Programme - Quality Improvement and Audit event hosted - Transitional care service specification approved - Proposed draft national bereavement care pathway for Wales for consultation - Service user engagement framework implemented |  |
| Priority 3 Implementation Network Implement Phase 2 of the Maternity and Neonatal Safety Support Programme | Quarter 1 (April -June) | - Quality Improvement: Design and implement all Wales Maternity and Neonatal Quality and Safety Day - Quality Improvement Maternal Care Pathway Commence planning for the standardisation of risk assessments - Quality Improvement Recognition and escalation of the deteriorating patient Implement Birmingham Symptom Specific Obstetric Triage across Health Boards | - Quality and safety day implemented and well attended - Plan for the standardisation of risk assessments - Implement Birmingham Symptom Specific Obstetric Triage | - Quality, Safety and Improvement colleagues and leads for SSP - SSP Safety champions - Health Boards - WAST |
|  | Quarter 2 (July-Sept) | - Quality Improvement Maternal Care Pathway planning the benchmarking of Freestanding and alongside midwifery units in Wales against published guidelines - Quality Improvement Maternal Care Pathway Review of ultrasound scanning standards and models for detecting small for gestational age babies to update All Wales guidance - Quality Improvement Maternal Care Pathway Standardise risk assessments pertaining to increased venous thromboembolism and gestational diabetes mellitus - Quality Improvement Recognition and escalation of the deteriorating patient learning event and consensus meeting to agree use and implementation of Maternity Early Warning Score (MEWS) for Wales for approval | - Completed review of ultrasound scanning standards and models - Agreed standardised risk assessments for increased VTE and GDM - Agreement on use and implementation of a Maternity Early Warning Score |  |
|  | Quarter 3 (Oct-Dec) | - Quality Improvement Maternal Care Pathway Standardise risk assessments pertaining to increased fetal surveillance and aspirin - Quality Improvement Maternal Care Pathway Undertake benchmarking of Freestanding and Alongside Midwifery Units in Wales against published guidelines - Quality Improvement Recognition and escalation of the deteriorating patient Approval and commence implementation of the All Wales standardised Maternity Early Warning Score chart across all Health Boards Approval and commence implementation of the Newborn Early Warning Track and Trigger 2 (NEWTT2) - Quality Improvement Perinatal optimisation and management of the neonate Develop a standardised review process for all babies born outside of the agreed gestational model including home births - Quality Improvement Perinatal optimisation and management of the neonate Benchmark current respiratory outcomes for pre-term babies in Wales and review current All Wales guidance for respiratory care - Quality Improvement development of work-based learning for transitional care, special care and neonatal outreach | - Agreed standardised risk assessments for increased fetal surveillance and aspirin - Approval and commence implementation of the All Wales standardised Maternity Early Warning Score chart across all Health Boards - Approval and commence implementation of the Newborn Early Warning Track and Trigger 2 (NEWTT2) - Agreed standardised risk for all babies born outside of the agreed gestational model - Benchmark report for current respiratory outcomes for pre-term babies - Proposal for work-based learning for transitional care, special care and neonatal outreach |  |
|  | Quarter 4 (Jan-Mar) | - Quality Improvement Recognition and escalation of the deteriorating patient Implementation of pathways for the recognition and escalation of the deteriorating patient (MEWS, NEWTT2) - Quality Improvement Perinatal optimisation and management of the neonate Undertake a national review of care pathways for babies with bilious vomiting to enable close partnership working between surgical neonatal intensive care units, transport services and all service providers | - Implementation of MEWS and NEWTT2 - Completed review of care pathways for babies with bilious vomiting and proposed recommendations |  |

### 2.3 	Risks

| Priority | Risks to implementation/delivery | Mitigations |
| --- | --- | --- |
| Priority 1, 2 and 3 | There is a risk that the Maternity and Neonatal Strategic Network and NHS Executive enabling team resources and capacity are not sufficient or available to carry out the planned actions outlined | - Prior planning with NHS Executive enabling functions so the timescales in the workplan are aligned and agreed to ensure sufficient resources - Network team members to attend induction to ensure understanding and knowledge of local procedures and policies to support implementation activities of network (e.g. effective recruitment processes) - Budget allocations and accurate forecasting to determine available resources and posts to - Resource and capacity planning of current team members against plan to ensure actions and timescales are achievable - Potential use of slippage in forecast budget to provide additional capacity/infrastructure to support some of the actions – e.g. communication plan |
| Priority 1 | There is a risk that there is no exit strategy and handover of the legacy operational roles and responsibility from the advisory maternity and neonatal network, specifically hosting and overseeing the operational delivery of the South Wales Neonatal Transport, Cymru inter-Hospital Acute Neonatal Transfer Service (CHANTS). Continuing these operational roles and responsibilities is outside the scope and remit of the strategic clinical networks and requires significant daily resource and oversight which will limit the capacity of the network to progress the strategic role and responsibilities and the planned actions required. | - Agreement between NHS Executive and JCC that there will be an exit strategy in place by March 2025 - Escalation of concerns of progress and timescales raised with JCC in May 2024, and written information received from JCC of commitment to meeting the timescale agreed - Support and help offered to JCC to inform options appraisal - Monitored and reported through the Clinical Reference Group with JCC in attendance and providing stakeholder updates |
| Priority 2 and Priority 3 | There is a risk that the current operational pressures on services means there will be limited stakeholder engagement and involvement and subsequent capacity and commitment to support the actions within the work programme. This would delay or influence the successful delivery of the workplan and objectives of the network | - Alignment of the workplan to support improvement of some of the key factors influencing current operational pressures to add value in the short and medium term and reduce burden on operational teams - Stakeholder engagement and involvement of the network team with operational leads to build effective relationships - Development of an effective communication plan to be clear about roles; responsibilities; proposed work programme and intended outcomes - Involvement and engagement with HEIW on the perinatal workforce plan - Resource and capacity planning of current team members and key stakeholders against plan to ensure actions and timescales are achievable given current operational constraints |
| Priority 2 | There is a risk in the ability to develop a Perinatal dashboard to support the effective monitoring and assurance of services due to organisations currently using different systems to collect information and use of different data definitions as well as lack of digital records to standardise and automate reporting | - Task and finish group and digital oversight group with support from the Health Intelligence team to work effectively with Health Boards to be clear what data is being reported and definitions being used - Working closely with Performance and Assurance to consider the data sources and options to pull data and clarity around definitions at system level - Working closely with Digital Health and Care Wales on aligning data definitions to agreed data standards - Supporting Health Boards and Digital Health and Care Wales on progress on a digital maternity record |

# 3.	Key enablers

| Key Enablers |  |  |  |
| --- | --- | --- | --- |
| Programme/ Enabling function | Priority 1 | Priority 2 | Priority 3 |
| Strategic Programme for Primary Care |  |  |  |
| Strategic Programme for Mental Health |  | X | X |
| Strategic Programme: Six goals for Urgent and Emergency Care |  | X | X |
| Strategic Programme for Planned Care |  |  |  |
| Digital, technology, innovation, and Value DTIV (NHS Executive) |  | X |  |
| Performance and Assurance (NHS Executive) |  | X | X |
| Financial Planning and Delivery (NHS Executive) | X |  |  |
| Quality, Safety, and Improvement (NHS Executive) |  | X | X |
| Workforce (HEIW) |  | X | X |
| Digital (DHCW) |  | X | X |
| Public Health Wales (Prevention) |  | X | X |

Over recent years there has been a number of high-profile maternity reports, both from across the UK and also reviewing the services provided in Wales and the corresponding experience and outcomes for babies; birthing women and their partners and families. These reports have highlighted poor outcomes and experiences and the long-lasting effects that these have upon individuals, families and communities. As a result of these reports there have been a number of whole system improvement recommendations and actions instigated for maternity and neonatal services at a local, regional and national level in Wales. This means that there are several NHS Executive interdependencies with a number of teams supporting different aspects of the improvement recommendations and providing system assurance. It is important that the Maternity and Neonatal Strategic Network has effective and close working relationships and implements matrix working with these enabling teams to ensure the work plan is seamless and joined up and avoids duplication or confusion to NHS Wales delivery organisations. The NHS Executive enabling teams include:

- Health Intelligence Service

- Digital, technology, innovation and Value (DTIV)

- Performance and Assurance

- Quality, Safety and Improvement

The strategic network will also have key interdependencies with teams within Public Health Wales including Antenatal Screening Wales and Health Improvement Teams leading on improvement work on Breastfeeding; the 1000 days programme and Early Years Framework for action.

The Strategic Network also has close alignment with a number of other Strategic Networks particularly the Women’s Health and Child Health Strategic Network and Perinatal Mental Health Network. It is recognised the Maternity and Neonatal Strategic Network interfaces with all condition-based networks.

In addition as key enablers, HEIW is working on the development of a Perinatal Workforce Strategy to address the workforce needs and DHCW is leading on the Digital Maternity Record. The Strategic Network is working closely with both organisations on both aspects to ensure these products align; complement and add value to the strategic work within action plan.

All of these key enabling teams are represented on the Maternity and Neonatal Strategic Network Clinical Reference Group.