## Slide 1: Hepatitis C National Projects: an update
Nicki Palmer
Public Health Wales

## Slide 2: Number of projects currently ongoing
Improving availability and access to DBST cards
Solutions surrounding third sector services not receiving DBST results
Establishing a cohort of reports around BBV testing in prisons
Notes: Task and Finish group for Testing and Procurement has been working on this.
Louise, Jonny, Stephen Barry, Dan Harman, Andrea Pace

## Slide 3: Improving availability and access to DBST cards
Procurement of DBST cards has not been straightforward
DBST cards have been purchased from a single supplier in the US
Experienced a number of issues with supply which has impacted on availability of cards to services
Additional manufacturer of DBST cards has been identified from within the EU
Notes: Jonny Evans has been leading the procurement side with support from the POCT and lab team on the validation of the cards

## Slide 4: Improving availability and access to DBST cards
New cards have been sourced and needed to undergo a validation process to ensure the validity of results
Validation process has taken time and is now complete
Next step is for the manufacturer and the cards to be added to Oracle to enable NHS services to order these directly
Huge thank you to our colleagues in the lab and procurement for this progress
Notes: The POCT and lab teams have been key to the validation of the cards
Definitely a team approach to this!

## Slide 5: Third sector services not receiving DBST results
Well recognised issue across third sector services
Currently working on short and sustainable longer-term solutions

## Slide 6: Finding solutions
In identifying solutions, first needed to know the causes
Multi-pronged approach to solutions
Need to know who sent in the test and ensure this is accurately recorded in LIMS
Each service needs its own unique code in LIMS
Notes: Causes:
Tests not arriving at the lab
Tests being rejected but this not being fed back to services – could be expired DBST cards, discrepancies in patient details on the request form and DBST card
Tests processed but no result posted out.
Test processed, result posted out but not received.
Test processed but analyser error leading to no result being available. This not being fed back to services.
In knowing who sent the test, the result can be sent to the correct postal address.
To do this – each service needs a unique code

## Slide 7: Short term solutions
Worked alongside our PHW Substance Misuse colleagues
Worked with Area Planning Boards to get an accurate picture of current providers
Collated accurate list of provider services, with up-to-date postal addresses, contact email and phone number
Notes: Worked with Dan Harman as this tied in with a piece of work he was already involved in
2 birds 1 stone

## Slide 8: Short term solutions: LIMS
Using existing information already held
Able to establish:
New providers with no information held in LIMS
Existing providers who have moved premises
Work with our LIMS and IT colleagues
Awaiting progress update
Update or amend information currently held
Add new services
Remove services no longer commissioned
Give each service a unique identifying code
Notes: Spreadsheet of services within each health board provided to LIMS team

## Slide 9: Longer term solutions
Looking for long term, sustainable solutions
Ideally need an electronic data sharing solution
Working with Information Governance and Digital Health and Care Wales to progress a solution
Notes: Not within our control
Not going to be any quick wins
Will be costly
Raised to IG and DHCW that there are issues relating to clinical governance with this issue

## Slide 10: BBV reporting in prisons
Healthcare staff are working really hard on the Hepatitis C agenda
Making great strides with testing and towards elimination
This work needs to be recognised and captured
Our colleagues in England have already established systems for reporting progress towards elimination
Notes: Last piece of national work in progress currently

## Slide 11: BBV reporting in prisons
Need to know what reporting system and structure is needed in Wales (still work in progress)
Collaborate with colleagues from England, learn from their experience
Develop a cohort of reports using SystmOne that will enable each prison to evaluate their testing processes and enable assessment against elimination criteria
Notes: Not appropriate to just transfer the whole reporting system and structure from England to Wales
We need to have our own structure, that will be worked on with the Data Task and Finish group that PHW will be setting up

## Slide 12: BBV reporting in prisons: current progress
Cohort of reports established
Need evaluating against existing data to assess validity
Plan to roll out to prisons across Wales in the next few weeks
Will be work in progress while wider reporting systems are established
Notes: Huge thanks to Craig from Spectrum Health and Hannah from Berwyn

## Slide 13: Any questions?
Email:
Nicki.palmer@wales.nhs.uk